## Gantt Chart
Intelligent Diabetes Risk Predictor — Project Gantt Chart
ID | Phase | Task Name | Start | Finish | Duration (weeks) | % Done | W1 01 Jun | W2 08 Jun | W3 15 Jun | W4 22 Jun | W5 29 Jun | W6 06 Jul | W7 13 Jul | W8 20 Jul | W9 27 Jul | W10 03 Aug | W11 10 Aug | W12 17 Aug | W13 24 Aug | W14 31 Aug
◀ Phase 1 ▶
1 | Phase 1 | Requirements Analysis & Documentation | 01-Jun-2026 | 12-Jun-2026 | 2 | 100% | 100%
2 | Phase 1 | Gather functional requirements | 01-Jun-2026 | 05-Jun-2026 | 1 | 100% | 100%
3 | Phase 1 | Document non-functional requirements | 01-Jun-2026 | 12-Jun-2026 | 2 | 100% | 100%
4 | Phase 1 | ◆ SRS document finalized | 08-Jun-2026 | 12-Jun-2026 | 1 | 100%
◀ Phase 2 ▶
5 | Phase 2 | System & Database Design | 15-Jun-2026 | 26-Jun-2026 | 2 | 75% |  |  | 75%
6 | Phase 2 | System architecture design | 15-Jun-2026 | 19-Jun-2026 | 1 | 75% |  |  | 75%
7 | Phase 2 | Database schema design | 15-Jun-2026 | 26-Jun-2026 | 2 | 50% |  |  | 50%
8 | Phase 2 | ML pipeline blueprint | 22-Jun-2026 | 26-Jun-2026 | 1 | 50% |  |  |  | 50%
◀ Phase 3 ▶
9 | Phase 3 | Dataset Acquisition & Preprocessing | 22-Jun-2026 | 03-Jul-2026 | 2 | 50% |  |  |  | 50%
10 | Phase 3 | Download Kaggle diabetes dataset | 22-Jun-2026 | 26-Jun-2026 | 1 | 100% |  |  |  | 100%
11 | Phase 3 | Data cleaning & transformation | 22-Jun-2026 | 03-Jul-2026 | 2 | 50% |  |  |  | 50%
12 | Phase 3 | Train/test split (70/30) | 29-Jun-2026 | 03-Jul-2026 | 1 | 0%
◀ Phase 4 ▶
13 | Phase 4 | EDA & Visualization | 29-Jun-2026 | 10-Jul-2026 | 2 | 0%
14 | Phase 4 | Exploratory data analysis | 29-Jun-2026 | 10-Jul-2026 | 2 | 0%
15 | Phase 4 | Summary statistics & graphs | 06-Jul-2026 | 10-Jul-2026 | 1 | 0%
◀ Phase 5 ▶
16 | Phase 5 | ML Model Development – Iteration 1 | 06-Jul-2026 | 24-Jul-2026 | 3 | 0%
17 | Phase 5 | Logistic Regression model | 06-Jul-2026 | 17-Jul-2026 | 2 | 0%
18 | Phase 5 | Decision Tree model | 13-Jul-2026 | 17-Jul-2026 | 1 | 0%
19 | Phase 5 | SVM model | 13-Jul-2026 | 24-Jul-2026 | 2 | 0%
20 | Phase 5 | Neural Network model | 13-Jul-2026 | 24-Jul-2026 | 2 | 0%
◀ Phase 6 ▶
21 | Phase 6 | Model Evaluation & Selection | 20-Jul-2026 | 31-Jul-2026 | 2 | 0%
22 | Phase 6 | Accuracy / Precision / Recall / F1 | 20-Jul-2026 | 31-Jul-2026 | 2 | 0%
23 | Phase 6 | Confusion matrix generation | 20-Jul-2026 | 31-Jul-2026 | 2 | 0%
24 | Phase 6 | ◆ Best model selected & saved | 27-Jul-2026 | 31-Jul-2026 | 1 | 0%
◀ Phase 7 ▶
25 | Phase 7 | Risk Factor Analysis & Recommendations | 27-Jul-2026 | 07-Aug-2026 | 2 | 0%
26 | Phase 7 | Feature importance / SHAP values | 27-Jul-2026 | 07-Aug-2026 | 2 | 0%
27 | Phase 7 | Personalized recommendation engine | 03-Aug-2026 | 07-Aug-2026 | 1 | 0%
◀ Phase 8 ▶
28 | Phase 8 | Dashboard & Report Generation | 03-Aug-2026 | 14-Aug-2026 | 2 | 0%
29 | Phase 8 | Build visualization dashboard | 03-Aug-2026 | 14-Aug-2026 | 2 | 0%
30 | Phase 8 | PDF / CSV report export | 10-Aug-2026 | 14-Aug-2026 | 1 | 0%
◀ Phase 9 ▶
31 | Phase 9 | Longitudinal Tracking & Admin Module | 10-Aug-2026 | 21-Aug-2026 | 2 | 0%
32 | Phase 9 | Health record history store | 10-Aug-2026 | 21-Aug-2026 | 2 | 0%
33 | Phase 9 | Admin model management panel | 10-Aug-2026 | 21-Aug-2026 | 2 | 0%
◀ Phase 10 ▶
34 | Phase 10 | Testing & Quality Assurance | 17-Aug-2026 | 28-Aug-2026 | 2 | 0%
35 | Phase 10 | Unit & integration testing | 17-Aug-2026 | 28-Aug-2026 | 2 | 0%
36 | Phase 10 | Model evaluation validation | 24-Aug-2026 | 28-Aug-2026 | 1 | 0%
37 | Phase 10 | User acceptance testing | 24-Aug-2026 | 28-Aug-2026 | 1 | 0%
◀ Phase 11 ▶
38 | Phase 11 | Deployment & Final Documentation | 24-Aug-2026 | 04-Sep-2026 | 2 | 0%
39 | Phase 11 | System deployment | 24-Aug-2026 | 04-Sep-2026 | 2 | 0%
40 | Phase 11 | Final SRS & user manual | 31-Aug-2026 | 04-Sep-2026 | 1 | 0%
41 | Phase 11 | ◆ Project delivery milestone | 31-Aug-2026 | 04-Sep-2026 | 1 | 0%
LEGEND: |  | Not started |  | In progress |  | Complete |  | Milestone |  | Current week