## Gantt Chart
Intelligent Diabetes Risk Predictor — Project Gantt Chart
VU Portal Deadlines · SRS: 25 May 2026 · Design: 24 Jul 2026 · Prototype: 26 Aug 2026 · Final: 27 Oct 2026 · Group: S26PROJECTA7FFD · Supervisor: Komal Khawer
| Task |  |  |  | May 2026 |  |  | June 2026 |  |  |  |  | July 2026 |  |  |  | August 2026 |  |  |  |  | September 2026 |  |  |  | October 2026
# | Task / Deliverable | Start | Due Date | Days | W1 11/05 | W2 18/05 | W3 25/05 | W4 01/06 | W5 08/06 | W6 15/06 | W7 22/06 | W8 29/06 | W9 06/07 | W10 13/07 | W11 20/07 | W12 27/07 | W13 03/08 | W14 10/08 | W15 17/08 | W16 24/08 | W17 31/08 | W18 07/09 | W19 14/09 | W20 21/09 | W21 28/09 | W22 05/10 | W23 12/10 | W24 19/10 | W25 26/10
| ◀ SRS DOCUMENT ▶ | [5 empty] | ▼ DUE
1 | Requirements Analysis & Documentation | 11 May 2026 | 12 May 2026 | 2
2 | Gather functional requirements | 13 May 2026 | 14 May 2026 | 2
3 | Document non-functional requirements | 15 May 2026 | 16 May 2026 | 2
4 | Use Case Diagram & Scenarios | 17 May 2026 | 18 May 2026 | 2
5 | Process Model (VU Hybrid) | 19 May 2026 | 20 May 2026 | 2
6 | Work Plan / Gantt Chart | 21 May 2026 | 22 May 2026 | 2
7 | ◆ SRS document finalized | 24 May 2026 | 24 May 2026 | 1 |  | ◆
| ◀ DESIGN DOCUMENT ▶ | [13 empty] | ▼ DUE
8 | System & Database Design | 26 May 2026 | 29 May 2026 | 4 |  |  | 0%
9 | System architecture design | 30 May 2026 | 02 Jun 2026 | 4 |  |  |  | 0%
10 | Database schema design | 03 Jun 2026 | 06 Jun 2026 | 4 |  |  |  | 0%
11 | ML pipeline blueprint | 07 Jun 2026 | 10 Jun 2026 | 4 |  |  |  |  | 0%
12 | Dataset Acquisition & Preprocessing | 11 Jun 2026 | 14 Jun 2026 | 4 |  |  |  |  | 0%
13 | Download Kaggle diabetes dataset | 15 Jun 2026 | 18 Jun 2026 | 4 | [5 empty] | 0%
14 | Data cleaning & transformation | 19 Jun 2026 | 22 Jun 2026 | 4 | [5 empty] | 0%
15 | Train/test split (70/30) | 23 Jun 2026 | 26 Jun 2026 | 4 | [6 empty] | 0%
16 | EDA & Visualization | 27 Jun 2026 | 30 Jun 2026 | 4 | [7 empty] | 0%
17 | Exploratory data analysis | 01 Jul 2026 | 04 Jul 2026 | 4 | [7 empty] | 0%
18 | Summary statistics & graphs | 05 Jul 2026 | 08 Jul 2026 | 4 | [8 empty] | 0%
19 | ◆ Design Document finalized | 12 Jul 2026 | 12 Jul 2026 | 1 | [8 empty] | ◆
| ◀ PROTOTYPE PHASE ▶ | [18 empty] | ▼ DUE
20 | ML Model Development – Iteration 1 | 25 Jul 2026 | 26 Jul 2026 | 2
21 | Logistic Regression model | 27 Jul 2026 | 28 Jul 2026 | 2
22 | Decision Tree model | 29 Jul 2026 | 30 Jul 2026 | 2
23 | SVM model | 31 Jul 2026 | 01 Aug 2026 | 2
24 | Neural Network model | 02 Aug 2026 | 03 Aug 2026 | 2
25 | Model Evaluation & Selection | 04 Aug 2026 | 05 Aug 2026 | 2
26 | Accuracy / Precision / Recall / F1 | 06 Aug 2026 | 07 Aug 2026 | 2
27 | Confusion matrix generation | 08 Aug 2026 | 09 Aug 2026 | 2
28 | Risk Factor Analysis | 10 Aug 2026 | 11 Aug 2026 | 2
29 | Feature importance / SHAP values | 12 Aug 2026 | 13 Aug 2026 | 2
30 | Personalized recommendation engine | 14 Aug 2026 | 15 Aug 2026 | 2
31 | ◆ Best model selected & saved | 17 Aug 2026 | 17 Aug 2026 | 1 | [14 empty] | ◆
| ◀ FINAL DELIVERABLE ▶ | [27 empty] | ▼ DUE
32 | Dashboard & Report Generation | 27 Aug 2026 | 30 Aug 2026 | 4 | [15 empty] | 0%
33 | Build visualization dashboard | 31 Aug 2026 | 03 Sep 2026 | 4 | [16 empty] | 0%
34 | PDF / CSV report export | 04 Sep 2026 | 07 Sep 2026 | 4 | [16 empty] | 0%
35 | Longitudinal Tracking & Admin Module | 08 Sep 2026 | 11 Sep 2026 | 4 | [17 empty] | 0%
36 | Health record history store | 12 Sep 2026 | 15 Sep 2026 | 4 | [18 empty] | 0%
37 | Admin model management panel | 16 Sep 2026 | 19 Sep 2026 | 4 | [18 empty] | 0%
38 | Testing & Quality Assurance | 20 Sep 2026 | 23 Sep 2026 | 4 | [19 empty] | 0%
39 | Unit & integration testing | 24 Sep 2026 | 27 Sep 2026 | 4 | [19 empty] | 0%
40 | Model evaluation validation | 28 Sep 2026 | 01 Oct 2026 | 4 | [20 empty] | 0%
41 | User acceptance testing | 02 Oct 2026 | 05 Oct 2026 | 4 | [20 empty] | 0%
42 | Deployment & Final Documentation | 06 Oct 2026 | 09 Oct 2026 | 4 | [21 empty] | 0%
43 | System deployment | 10 Oct 2026 | 13 Oct 2026 | 4 | [22 empty] | 0%
44 | Final SRS & user manual | 14 Oct 2026 | 17 Oct 2026 | 4 | [22 empty] | 0%
45 | ◆ Project delivery milestone | 21 Oct 2026 | 21 Oct 2026 | 1 | [23 empty] | ◆
LEGEND | [5 empty] | SRS Document |  | Design Document |  | Prototype Phase |  | Final Deliverable |  | In Progress |  | Complete |  | Current Week |  | Deadline Week |  | ◆ Milestone